## Sheet1
Sprint backlog | Sprint task | Volunteer | Initial estimate | remaining as of day...
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6
Grunnleggende oppsett | Database | Gaute, Vetle | 8 | 4 | 0 | 0 | 0 | 0 | 0 |  | 83
| Backend skeleton | Tore | 5 | 0 | 0 | 0 | 0 | 0 | 0
| Frontend skeleton | Alexander | 5 | 0 | 0 | 0 | 0 | 0 | 0
| CI pipeline (including debug) | Tore | 3 | 1 | 1 | 0 | 0 | 0 | 0
| Sette opp klienttester | Randi, Maria | 8 | 8 | 8 | 8 | 6 | 4 | 2
| Sette opp testing av endepunkt | Randi, Maria | 8 | 8 | 8 | 8 | 6 | 4 | 1
| Sette opp DAO-tester | Tore | 2 | 0 | 0 | 0 | 0 | 0 | 0
| state | Randi | 8 | 0 | 0 | 0 | 0 | 0 | 0
| REST-API | Tore, Jørgen | 4 | 3 | 5 | 5 | 4.5 | 4 | 3
| React Componenter | Alle (Main Alexander/Jørgen) | 30 | 20 | 15 | 10 | 5 | 0 | 0
| GIT - oppsett | Tore | 2 | 0 | 0 | 0 | 0 | 0 | 0
Registrere bruker | Lage endepunkt server | Tore, Jørgen, Maria | 2 | 1 | 0 | 0 | 0 | 0 | 0 |  | 36
| Hashfunksjonen | Jørgen | 7 | 1 | 0 | 0 | 0 | 0 | 0
| Javascript som snakker med UI | Jørgen | 4 | 0 | 0 | 0 | 0 | 0 | 0
| User interface | Alexander | 6 | 0 | 0 | 0 | 0 | 0 | 0
| Server forespørselen | Alexander | 4 | 2 | 0 | 0 | 0 | 0 | 0
| Tester | Tore | 3 | 2 | 2 | 2 | 2 | 2 | 2
| Dokumentasjon | - | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Lage databasetabellen | Gaute, Tore | 2 | 0 | 0 | 0 | 0 | 0 | 0
Innlogging | Lage databasetabellen | Gaute, Tore | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 45
| Lage endepunkt server | Maria, Tore | 5 | 5 | 5 | 0 | 0 | 0 | 0
| JSON Webtoken-stuff | Tore, Jørgen, Maria | 20 | 20 | 10 | 5 | 0 | 0 | 0
| Javascript som snakker med UI | Jørgen | 3 | 0 | 0 | 3 | 1 | 0 | 0
| Server forespørselen | Maria | 4 | 3.5 | 3.5 | 0 | 0 | 0 | 0
| User interface | Alexander | 3 | 1 | 0 | 0 | 0 | 0 | 0
| Dokumentasjon | - | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Tester |  | 3 | 3 | 1.5 | 1.5 | 1.5 | 1 | 1
Registrere arrangement | Arrangement visning | Alexander | 15 | 15 | 15 | 10 | 4 | 1 | 1 |  | 66
| Lage databasetabellen | Gaute, Tore | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Lage endepunkt server | Gaute, Chris, Tore | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Javascript som snakker med UI | Vetle | 2 | 2 | 0 | 0 | 0 | 0 | 0
| Server forespørselen | Vetle | 3 | 3 | 0 | 0 | 0 | 0 | 0
| User interface for å registere | Alexander, | 20 | 10 | 5 | 5 | 4 | 3 | 1
| Legge til mulighet for å laste opp filer | Maria | 10 | 10 | 10 | 0 | 0 | 0 | 0
| Tester | Gaute | 6 | 4 | 3 | 3 | 3 | 3 | 3
| Dokumentasjon | - | 6 | 6 | 6 | 6 | 6 | 6 | 6
Slette / arkivere arrangement | Dokumentasjon | - | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 22
| Tester | Gaute | 4 | 4 | 2 | 2 | 2 | 2 | 2
| Lage user interface | Christian | 3 | 3 | 3 | 3 | 0 | 2 | 1
| Lage endepunkt server | Christian | 5 | 5 | 5 | 0 | 0 | 0 | 0
| Javascript som snakker med UI | Christian | 5 | 5 | 5 | 2 | 0 | 0 | 0
| Server forespørselen | Christian | 3 | 3 | 3 | 0 | 0 | 0 | 0
Redigere arrangement | Dokumentasjon | - | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 12
| Server forespørselen | Christian | 2 | 2 | 0 | 0 | 0 | 0 | 0
| Lage user interface | Alexander, Christian | 4 | 4 | 4 | 3 | 3 | 2 | 1
| Tester | Christian, Gaute | 2 | 2 | 1 | 1 | 1 | 1 | 1
| Lage endepunkt server | Christian, Randi | 2 | 2 | 0 | 0 | 0 | 0 | 0
Avansert Søk | Lage User Interface | Gaute, Randi, Alexander | 5 | 5 | 5 | 3 | 3 | 3 | 1
| Tester | Tore, - | 4 | 4 | 4 | 4 | 3 | 3
| Dokumentasjon | Tore, Gaute | 3 | 3 | 3 | 3 | 2.5 | 2.5
| Lage Javascript logikk | Gaute | 8 | 8 | 8 | 5 | 3 | 1 | 0
| Server forespørselen |  | 3 | 3 | 3 | 3 | 3 | 3 | 2
| Lage endepunkter server | Tore | 7 | 7 | 7 | 7 | 3 | 3 | 1
Min side | Lage User Interface | Vetle, Trym | 18 | 18 | 18 | 9 | 4 | 2 | 0
| Tester | Vetle, Trym | 4 | 4 | 4 | 4 | 4 | 3 | 3
| Dokumentasjon | Vetle, Trym | 4 | 4 | 4 | 4 | 3 | 3 | 3
| Lage Javascript logikk | Vetle, Trym | 30 | 30 | 30 | 26 | 17 | 9 | 0
| Server forespørselen | Vetle, Trym | 8 | 8 | 8 | 8 | 6 | 2 | 0
| Lage endepunkter server | Vetle, Trym | 2 | 2 | 2 | 2 | 0 | 0 | 0
Legge til billettkategori | Lage user interface | Christian, Randi, Alexander | 10 | 10 | 10 | 8 | 4 | 4 | 4 |  | 22
| Tester |  | 2 | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
| Lage endepunkt server | Randi | 4 | 4 | 2 | 0 | 0 | 0 | 0
| Server forespørselen | Randi | 2 | 2 | 0 | 0 | 0 | 0 | 0
| Dokumentasjon | - | 4 | 4 | 4 | 4 | 4 | 4 | 4
|  |  | Burndown | 382 | 297.5 | 251.5 | 186 | 127 | 96 | 61.5
|  |  | Ideell linje | 382 | 318.3333 | 254.6667 | 191 | 127.3333 | 63.6667 | 0
|  |  | Dokumentasjon | 25 | 25 | 25 | 25 | 25 | 25 | 25
uuuuuh
￼
HeleneToday at 15:14
Er på vei til lunsj
￼
ToreToday at 15:14
vi skulle egentlig sendt den meldinga for en stund siden
Sprintmål: | Få på plass all hovedfunkjsonalitet i systemet